## Sheet1
|  | TERM 2 | [9 empty] | HOLIDAYS |  | TERM 3
Weeks |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 1 | 2 | 3 | 4 | 5
Preliminary Reseach | Introduction:
Title Page | bar: TERM 3 4 to TERM 3 5
Table of Contents | bar: TERM 3 4 to TERM 3 5
Project Proposal:
Initial Idea Development | bar: TERM 2 1 to TERM 2 5
Concept Selection | bar: TERM 2 1 to TERM 2 5
Statement of Intent | bar: TERM 2 1 to TERM 2 5
Design Management & Communication:
Time Management | bar: TERM 2 2 to TERM 2 3
Finance Management | bar: TERM 2 6
Research:
Existing Product Analysis | bar: TERM 2 1 to TERM 2 4
Materials | bar: TERM 2 2 to TERM 2 3
Processes | bar: TERM 2 2 to TERM 2 4
Resources | bar: TERM 2 3 to TERM 2 6
Justification of Materials, | bar: TERM 2 2 to TERM 2 6
Processes and Resources | bar: TERM 2 3 to TERM 2 5; TERM 3 5
Pre-Production | Design Development:
Concept Selection | bar: TERM 2 4 to TERM 2 6
Initial Sketches | bar: TERM 2 1 to TERM 2 6
Design Refinement | bar: TERM 2 7 to TERM 2 9
Script Writing | bar: TERM 2 7 to HOLIDAYS 2
Storyboarding | bar: TERM 2 7 to HOLIDAYS 2
Character Design/Costuming | bar: TERM 2 1 to TERM 2 3; TERM 2 7 to TERM 2 9
Map Modelling | bar: TERM 2 10 to HOLIDAYS 2
Shot List/Camera Testing | bar: TERM 2 10 to HOLIDAYS 2
rigging, animation | bar: TERM 2 10 to TERM 3 4
Production | Production:
Record of Production | bar: TERM 2 10 to TERM 3 5
Shoot Scene 1 | bar: TERM 2 10 to HOLIDAYS 1
Shoot Scene 2 | bar: HOLIDAYS 2
Post Production | Editing | bar: TERM 3 2 to TERM 3 5
Audio Effects | bar: TERM 3 2 to TERM 3 5
Soundtrack | bar: TERM 3 2
Additional Effects | bar: TERM 2 10; TERM 3 4 to TERM 3 5
Exporting | bar: TERM 3 2; TERM 3 4 to TERM 3 5
Safe Work Practices
Outsourcing | bar: TERM 3 1 to TERM 3 4
Links Between Planning and Production | bar: TERM 3 1 to TERM 3 5
Evidence of Solutions to Problems | bar: TERM 3 1 to TERM 3 5
Quality Control | bar: TERM 3 1 to TERM 3 5
Evaluation | Final Evaluation:
Evaluation in Relation to SOI | bar: TERM 3 5
Evaluation of Overall Quality | bar: TERM 3 5
Key: | Proposed:
Actual: